## Slide 1
Hampshire Health in Education
HealthEd Surveys 2025/26

## Slide 2: What is available?
For all Hampshire academy, maintained, special, independent and alternative provision settings:
Junior, Primary and All-through settings: Year 5 and Year 6 Pupil Hampshire HealthEd survey (accessible version)
Post-16 settings: Post-16 Hampshire HealthEd survey (accessible version)
All education settings and staff, all phases Early Years (EY) to Post-16: Hampshire HealthEd staff survey
Secondary settings: Secondary settings will be completing the #BeeWell survey in Years 7 and 10

## Slide 3
July August September October November December
Register interest by emailing: healtheducation@hants.gov.uk
Plan time to complete the survey e.g. in a lesson or tutorial for pupils, or a staff meeting for staff.
Inform staff and governors.
Send out parent/carer letter provided and record any opt-outs.
Half term
Survey launch and links sent
Complete the Year 5 and 6 surveys in lesson time. Share links with Post-16 learners and complete in tutor time. Share links with staff for the staff survey.
Survey closes
2025
2026
January February March April May
Public Health team analyses survey results.
Plan for survey results e.g. staff meeting, governors’ meeting, SIP, assembly to present to pupils/learners.
Survey reports sent to settings
Share the survey results and plan any actions with the support from the Hampshire Public Health team.
Survey Timeline

## Slide 4: About the surveys
All surveys should be completed online, using a computer or tablet, and should take around 20-25 minutes to complete.
Your setting will receive a confidential, aggregated school-level report of pupil responses in Spring 2026. District- and County-level reports will also be created and circulated later.
The staff survey data will be compiled into a county-level report only to inform future support offer.
The surveys ask questions on topics such as:
Emotional wellbeing
Healthy relationships and bullying
Healthy eating
Smoking and vaping
Confidence of staff
The results will help you prioritise school improvements, demonstrate good practice, and pupil and staff engagement.
The results will help the Public Health team prioritise support for education settings such as e-Learning training, online teaching resources, guidance and information.

## Slide 5: Thank you for your participation
Hampshire Health in Education (HHiE) is a Public Health programme for all education settings in Hampshire, from early years to Post-16. Our aim is to support you to take a Whole Setting Approach (WSA) to promote the health and wellbeing of children, young people, and families.
We do this by:
Supporting all staff to feel knowledgeable, confident, and skilled to support children and young people, and deliver health-related curricula.
Working in partnership with Children’s Services, health, and community organisations to provide a consistent, streamlined approach for education settings.
Monitoring the health and wellbeing of pupils and students through our Hampshire HealthEd School Surveys, and our work with #BeeWell.